## 📋 Task Timeline
🗂 CleanRoute-AI · Project Execution Timeline · Mar 31 – Apr 19, 2026
AI-Powered Smart Waste Management System ¦ Django · React · scikit-learn · Supabase
# | Phase | Task / Deliverable | Owner | Start | End | Days | Status | Priority | Dependencies | Notes
T1 | Phase 1 Project Setup | Repository initialization & project scaffolding | Maryam | 2026-03-31 | 2026-04-01 | 2 | ✅ Done | 🔴 Critical | — | GitHub repo created, folder structure set up
T2 | Phase 1 Project Setup | Django backend project init & virtual env | Maryam | 2026-03-31 | 2026-04-01 | 2 | ✅ Done | 🔴 Critical | — | venv, requirements.txt, manage.py configured
T3 | Phase 1 Project Setup | React frontend scaffolding (CRA + MUI) | Maryam | 2026-04-01 | 2026-04-02 | 2 | ✅ Done | 🔴 Critical | T2 | App.js, routing, dark theme configured
T4 | Phase 1 Project Setup | Supabase database setup & environment config | Maryam | 2026-04-01 | 2026-04-02 | 2 | ✅ Done | 🔴 Critical | T2 | .env files, DB connection tested
T5 | Phase 2 Backend Core | Custom user model (Admin / Citizen / Tester roles) | Maryam | 2026-04-02 | 2026-04-03 | 2 | ✅ Done | 🔴 Critical | T4 | users/models.py with role-based permissions
T6 | Phase 2 Backend Core | JWT authentication endpoints (login / refresh) | Maryam | 2026-04-03 | 2026-04-04 | 2 | ✅ Done | 🔴 Critical | T5 | SimpleJWT configured; token endpoints live
T7 | Phase 2 Backend Core | Complaint model, serializers & REST API | Maryam | 2026-04-04 | 2026-04-06 | 3 | ✅ Done | 🔴 Critical | T6 | CRUD + photo upload; DRF ViewSets
T8 | Phase 2 Backend Core | Admin interface & assignment API | Maryam | 2026-04-05 | 2026-04-06 | 2 | ✅ Done | 🟠 High | T7 | Django admin customised; assignment endpoints
T9 | Phase 3 AI / ML Engine | Computer vision waste detector (OpenCV) | Maryam | 2026-04-06 | 2026-04-08 | 3 | ✅ Done | 🔴 Critical | T7 | waste_detection.py — fill level & type (90% acc)
T10 | Phase 3 AI / ML Engine | Priority classifier (Decision Tree + Naive Bayes) | Maryam | 2026-04-07 | 2026-04-09 | 3 | ✅ Done | 🔴 Critical | T9 | URGENT/HIGH/MEDIUM/LOW; .pkl saved
T11 | Phase 3 AI / ML Engine | Route optimizer — K-Means clustering | Maryam | 2026-04-08 | 2026-04-10 | 3 | ✅ Done | 🔴 Critical | T10 | 25% time savings; cluster centroids exported
T12 | Phase 3 AI / ML Engine | Waste generation predictor (Linear Regression) | Maryam | 2026-04-08 | 2026-04-10 | 3 | ✅ Done | 🟠 High | T10 | 7-day forecast; RMSE 6.09 t
T13 | Phase 3 AI / ML Engine | Anomaly detector — Isolation Forest | Maryam | 2026-04-09 | 2026-04-11 | 3 | ✅ Done | 🟠 High | T10 | Illegal dumping hotspots; 88% accuracy
T14 | Phase 4 Frontend UI | Login page with JWT auth (Login.js) | Maryam | 2026-04-08 | 2026-04-09 | 2 | ✅ Done | 🔴 Critical | T6 | Role-based redirect after login
T15 | Phase 4 Frontend UI | Complaint submission form + photo upload (ComplaintForm.js) | Maryam | 2026-04-09 | 2026-04-11 | 3 | ✅ Done | 🔴 Critical | T14 | Integrates with /api/analyze-image/
T16 | Phase 4 Frontend UI | Interactive complaint map — Leaflet (ComplaintMap.js) | Maryam | 2026-04-10 | 2026-04-12 | 3 | ✅ Done | 🔴 Critical | T15 | Priority-coloured markers & route overlay
T17 | Phase 4 Frontend UI | Modern dashboard with Recharts (ModernDashboard.js) | Maryam | 2026-04-10 | 2026-04-12 | 3 | ✅ Done | 🟠 High | T16 | Stats cards, bar/line charts, workload pie
T18 | Phase 4 Frontend UI | Route optimizer visualisation (RouteOptimizer.js) | Maryam | 2026-04-11 | 2026-04-13 | 3 | ✅ Done | 🟠 High | T11 | Cluster map with estimated travel time
T19 | Phase 4 Frontend UI | 7-day waste prediction chart (WastePrediction.js) | Maryam | 2026-04-11 | 2026-04-13 | 3 | ✅ Done | 🟡 Medium | T12 | Line chart + RMSE indicator
T20 | Phase 4 Frontend UI | Anomaly detection map (AnomalyMap.js) | Maryam | 2026-04-12 | 2026-04-13 | 2 | ✅ Done | 🟡 Medium | T13 | Heatmap overlay for illegal-dump hotspots
T21 | Phase 4 Frontend UI | Admin & Tester dashboards | Maryam | 2026-04-12 | 2026-04-14 | 3 | ✅ Done | 🟠 High | T17 | Role-gated views; assign/close complaint flows
T22 | Phase 5 Integration & Testing | Backend–Frontend API integration | Maryam | 2026-04-13 | 2026-04-15 | 3 | ✅ Done | 🔴 Critical | P4 done | Axios interceptors, CORS, JWT header injection
T23 | Phase 5 Integration & Testing | ML model integration & end-to-end flow | Maryam | 2026-04-13 | 2026-04-15 | 3 | ✅ Done | 🔴 Critical | P3 done | test_all_ml_models.py; run_all_tests.py
T24 | Phase 5 Integration & Testing | Unit & integration tests (Django + React) | Maryam | 2026-04-14 | 2026-04-16 | 3 | ✅ Done | 🟠 High | T22,T23 | pytest + npm test; CI via GitHub Actions
T25 | Phase 5 Integration & Testing | Bug fixes & performance optimisation | Maryam | 2026-04-15 | 2026-04-16 | 2 | ✅ Done | 🟠 High | T24 | Slow prediction fix; image-size guard (<10 MB)
T26 | Phase 6 Deployment & Docs | Backend deployment to Render | Maryam | 2026-04-16 | 2026-04-17 | 2 | ✅ Done | 🔴 Critical | P5 done | gunicorn, env vars, health endpoint verified
T27 | Phase 6 Deployment & Docs | Frontend deployment to Vercel | Maryam | 2026-04-16 | 2026-04-17 | 2 | ✅ Done | 🔴 Critical | T26 | npm run build → vercel --prod; live URL tested
T28 | Phase 6 Deployment & Docs | Technical documentation (docs/ folder, README) | Maryam | 2026-04-17 | 2026-04-18 | 2 | ✅ Done | 🟡 Medium | T26,T27 | 7 markdown files covering arch, API, deployment
T29 | Phase 6 Deployment & Docs | Final project report PDF & Medium article | Maryam | 2026-04-18 | 2026-04-19 | 2 | ✅ Done | 🟡 Medium | T28 | Clean_Route_AI_Report.pdf; Medium blog post
T30 | Phase 6 Deployment & Docs | Demo video & project handover | Maryam | 2026-04-19 | 2026-04-19 | 1 | ✅ Done | 🟡 Medium | T29 | Full walkthrough video; GitHub repo finalised
📊 PROJECT SUMMARY
Total Tasks | 30
Project Duration | 20 days (Mar 31 – Apr 19)
Phases | 6
Status | 100 % Complete ✅
Django · React · scikit-learn · Supabase · Vercel · Render

## 📊 Gantt Chart
📊 CleanRoute-AI · Gantt Chart · Mar 31 – Apr 19, 2026
Each coloured bar represents active work days for that task
[5 empty] | ◀ MARCH ▶ | ◀ APRIL ▶
# | Phase | Task | Owner | Days | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
T1 | Phase 1 | Repository initialization & project scaffolding | Maryam | 2 | ▶ | ■
T2 | Phase 1 | Django backend project init & virtual env | Maryam | 2 | ▶ | ■
T3 | Phase 1 | React frontend scaffolding (CRA + MUI) | Maryam | 2 |  | ▶ | ■
T4 | Phase 1 | Supabase database setup & environment config | Maryam | 2 |  | ▶ | ■
T5 | Phase 2 | Custom user model (Admin / Citizen / Tester roles) | Maryam | 2 |  |  | ▶ | ■
T6 | Phase 2 | JWT authentication endpoints (login / refresh) | Maryam | 2 |  |  |  | ▶ | ■
T7 | Phase 2 | Complaint model, serializers & REST API | Maryam | 3 |  |  |  |  | ▶ |  | ■
T8 | Phase 2 | Admin interface & assignment API | Maryam | 2 | [5 empty] | ▶ | ■
T9 | Phase 3 | Computer vision waste detector (OpenCV) | Maryam | 3 | [6 empty] | ▶ |  | ■
T10 | Phase 3 | Priority classifier (Decision Tree + Naive Bayes) | Maryam | 3 | [7 empty] | ▶ |  | ■
T11 | Phase 3 | Route optimizer — K-Means clustering | Maryam | 3 | [8 empty] | ▶ |  | ■
T12 | Phase 3 | Waste generation predictor (Linear Regression) | Maryam | 3 | [8 empty] | ▶ |  | ■
T13 | Phase 3 | Anomaly detector — Isolation Forest | Maryam | 3 | [9 empty] | ▶ |  | ■
T14 | Phase 4 | Login page with JWT auth (Login.js) | Maryam | 2 | [8 empty] | ▶ | ■
T15 | Phase 4 | Complaint submission form + photo upload (ComplaintForm… | Maryam | 3 | [9 empty] | ▶ |  | ■
T16 | Phase 4 | Interactive complaint map — Leaflet (ComplaintMap.js) | Maryam | 3 | [10 empty] | ▶ |  | ■
T17 | Phase 4 | Modern dashboard with Recharts (ModernDashboard.js) | Maryam | 3 | [10 empty] | ▶ |  | ■
T18 | Phase 4 | Route optimizer visualisation (RouteOptimizer.js) | Maryam | 3 | [11 empty] | ▶ |  | ■
T19 | Phase 4 | 7-day waste prediction chart (WastePrediction.js) | Maryam | 3 | [11 empty] | ▶ |  | ■
T20 | Phase 4 | Anomaly detection map (AnomalyMap.js) | Maryam | 2 | [12 empty] | ▶ | ■
T21 | Phase 4 | Admin & Tester dashboards | Maryam | 3 | [12 empty] | ▶ |  | ■
T22 | Phase 5 | Backend–Frontend API integration | Maryam | 3 | [13 empty] | ▶ |  | ■
T23 | Phase 5 | ML model integration & end-to-end flow | Maryam | 3 | [13 empty] | ▶ |  | ■
T24 | Phase 5 | Unit & integration tests (Django + React) | Maryam | 3 | [14 empty] | ▶ |  | ■
T25 | Phase 5 | Bug fixes & performance optimisation | Maryam | 2 | [15 empty] | ▶ | ■
T26 | Phase 6 | Backend deployment to Render | Maryam | 2 | [16 empty] | ▶ | ■
T27 | Phase 6 | Frontend deployment to Vercel | Maryam | 2 | [16 empty] | ▶ | ■
T28 | Phase 6 | Technical documentation (docs/ folder, README) | Maryam | 2 | [17 empty] | ▶ | ■
T29 | Phase 6 | Final project report PDF & Medium article | Maryam | 2 | [18 empty] | ▶ | ■
T30 | Phase 6 | Demo video & project handover | Maryam | 1 | [19 empty] | ▶
LEGEND
P1 – Setup |  |  | P2 – Backend |  |  | P3 – AI/ML |  |  | P4 – Frontend |  |  | P5 – Integration |  |  | P6 – Deployment |  |  | Weekend